## Config
SMB Commerce OS — Build Calendar Configuration
Set the two blue cells below. Every date in this workbook recalculates from them.
Setting | Value | Notes
Build start date | 2026-09-14 | First build day. Must be a weekday.
Build days per week | 3 | 3 = part-time (realistic alongside other commitments). 5 = full-time.
Derived
Total build days
MVP gate date (D136, end of Phase 7)
Final day date (D176)
Elapsed weeks to MVP gate
Elapsed weeks total
Legend
Blue text on yellow fill | Input cell — you edit these
Black text | Formula — do not overwrite
Green row fill (Daily Plan) | Phase gate day
Orange row fill (Daily Plan) | MVP gate (D136)
Status values | Not started / In progress / Done / Carried / Blocked
Dates are computed as WORKDAY(start, (day-1) x 5 / days_per_week), so the schedule stretches
across calendar weeks according to your chosen cadence. Holidays are not modelled — carry cards as needed.

## Phase Summary
Phase Summary
Dates recalculate from the Config sheet. A gate passes when its acceptance test passes in CI, not when the date arrives.
Phase | Name | First day | Last day | Days | Start date | End date | Gate | Gate acceptance criterion
0 | Foundations & Security Baseline | D001 | D012 | 12 |  |  | G0 | Repo, CI, and security gates green on an empty app
1 | Domain Model & Database | D013 | D030 | 18 |  |  | G1 | Schema migrates on both dialects; tenant isolation proven by test
2 | Catalog & Product Inventory | D031 | D044 | 14 |  |  | G2 | A product can be listed, stocked, and sold
3 | Availability Engine & Services | D045 | D062 | 18 |  |  | G3 | No double-booking under real concurrent load, both dialects
4 | Rentals, Deposits & Returns | D063 | D086 | 24 |  |  | G4 | Full rental lifecycle including deposit settlement
5 | Payments — Stripe Connect | D087 | D100 | 14 |  |  | G5 | Money moves correctly in all three modes
6 | Merchant Dashboard (Web) | D101 | D120 | 20 |  |  | G6 | A merchant can operate unaided
7 | Customer Storefront (Web) | D121 | D136 | 16 |  |  | G7 | MVP GATE — pilot-capable, web only
8 | Mobile Application | D137 | D152 | 16 |  |  | G8 | Parity for customer flows on iOS and Android
9 | Security Hardening & Compliance Pack | D153 | D166 | 14 |  |  | G9 | Pen test clean; compliance evidence assembled
10 | Pilot Readiness & Launch | D167 | D176 | 10 |  |  | G10 | First merchant live
TOTAL

## Daily Plan
Daily Plan — one card per build day
One card, one day, one merge. If a card cannot be finished and verified in a day it was scoped wrong — split it before starting. Mark Carried rather than extending a card silently.
Day | Date | Ph | Phase | Epic | Task | Deliverable | Acceptance criteria | Security check | Status | Hrs | Notes | Card (prompt) | Log | Est. Duration (AI session)
1 |  | 0 | Foundations & Security Baseline | Toolchain | Initialize monorepo | pnpm workspaces + Turborepo; apps/ and packages/ per ADR-001 | `pnpm install` succeeds; workspace graph resolves | No secrets in initial commit; .gitignore covers .env | Not started |  |  | D001 | D001 | 1.0h
2 |  | 0 | Foundations & Security Baseline | Toolchain | TypeScript strict configuration | Shared tsconfig package, strict mode, no implicit any | `tsc --noEmit` passes across all packages | Strict null checks reduce a class of runtime defects | Not started |  |  | D002 | D002 | 1.0h
3 |  | 0 | Foundations & Security Baseline | Toolchain | Lint and format rules | ESLint + Prettier; custom rule banning raw SQL outside packages/db | Lint fails on a deliberate raw-SQL violation in apps/api | Rule enforces the dialect + tenant-scoping boundary | Not started |  |  | D003 | D003 | 1.0h
4 |  | 0 | Foundations & Security Baseline | Toolchain | Test harness | Vitest configured; coverage thresholds set per 10_secure_sdlc | `pnpm test` runs; coverage gate fails below threshold | Domain package threshold set to 95% | Not started |  |  | D004 | D004 | 1.0h
5 |  | 0 | Foundations & Security Baseline | CI/CD | CI pipeline skeleton | Workflow: install, lint, typecheck, test on every PR | Pipeline green on an empty app | Frozen lockfile prevents dependency substitution | Not started |  |  | D005 | D005 | 1.0h
6 |  | 0 | Foundations & Security Baseline | CI/CD | Secret scanning | gitleaks in pre-commit hook and CI | Planted test secret fails the build | Any finding fails build; rotation procedure documented | Not started |  |  | D006 | D006 | 1.0h
7 |  | 0 | Foundations & Security Baseline | CI/CD | Dependency scanning and SBOM | Scanner in CI; SBOM generated and retained as artifact | Build fails on a high/critical with a fix available | SBOM is the dependency-inventory evidence for control ID | Not started |  |  | D007 | D007 | 1.0h
8 |  | 0 | Foundations & Security Baseline | CI/CD | SAST | CodeQL or Semgrep in CI | Build fails on high/critical finding | Static analysis before any application code exists | Not started |  |  | D008 | D008 | 1.0h
9 |  | 0 | Foundations & Security Baseline | CI/CD | Branch protection and PR template | Protection rules; PR template with self-review checklist; conventional commits | Direct push to main rejected | Self-review checklist is the CC8 change-management evidence | Not started |  |  | D009 | D009 | 1.0h
10 |  | 0 | Foundations & Security Baseline | Security foundation | Native AuthProvider implementation | AuthProvider interface + NativeAuthProvider (Argon2id, sessions, rate limiting) per ADR-002; Auth0 deferred, interface keeps swap-in possible later | Register/login/authenticated-route/logout/reset-initiation all pass against NativeAuthProvider; test proves no module imports NativeAuthProvider directly except via the interface | Argon2id hashing, no plaintext/bcrypt; login+reset rate-limited from this card; sessions revocable server-side; see docs/adr/ADR-002-authentication-provider.md | Not started |  | Revised per ADR-002 (2026-09-07): was 'Identity provider spike / OIDC PKCE'. Founder decision: native auth now, Auth0-ready interface, Auth0 wired in later. | D010 | D010 | 4.0h
11 |  | 0 | Foundations & Security Baseline | Security foundation | Security policy set | /docs/compliance/policies drafted from GRC templates | Six core policies committed and reviewed via PR | Policies in version control give change history and effective dates | Not started |  |  | D011 | D011 | 1.0h
12 |  | 0 | Foundations & Security Baseline | Security foundation | Threat model, IR plan, subprocessors — GATE G0 | Threat model reviewed; incident-response.md; subprocessors.md | G0 record filed; all CI gates green on empty app | Baseline threat model recorded before any feature exists | Not started |  |  | D012 | D012 | 2.5h
13 |  | 1 | Domain Model & Database | Database foundation | SQLite connection layer | Drizzle + SQLite; WAL, foreign_keys ON, busy_timeout set | PRAGMA values asserted by a startup test | foreign_keys ON — off by default in SQLite, a silent divergence from PG | Not started |  |  | D013 | D013 | 2.0h
14 |  | 1 | Domain Model & Database | Database foundation | PostgreSQL connection and CI matrix | PG config; CI runs the suite against both dialects | Both dialect jobs green | Portability failure is caught the day it is written | Not started |  |  | D014 | D014 | 3.0h
15 |  | 1 | Domain Model & Database | Database foundation | Migration tooling | drizzle-kit; forward-only policy; both-dialect migration check in CI | A PG-incompatible migration fails CI | Migration review is part of the security review triggers | Not started |  |  | D015 | D015 | 3.0h
16 |  | 1 | Domain Model & Database | Database foundation | Core utilities | UUIDv7 generator; Money minor-unit value object; UTC time helpers | Property tests: no float money; all timestamps UTC | Money as integer minor units — floats are unacceptable for money | Not started |  |  | D016 | D016 | 2.0h
17 |  | 1 | Domain Model & Database | Tenancy | TenantContext and repository base | TenantContext type; base class injecting merchant_id predicate | Repository method without ctx is a compile error | Control #1 — tenant isolation, layer 2 (type system) | Not started |  |  | D017 | D017 | 2.0h
18 |  | 1 | Domain Model & Database | Tenancy | Schema: tenancy tables | merchants, users, merchant_users, locations | Migrations apply on both dialects | No password column on users — auth is delegated | Not started |  |  | D018 | D018 | 3.0h
19 |  | 1 | Domain Model & Database | Tenancy | Repository: merchants and locations | Scoped repository methods | CRUD works; scoping predicate present in every query | Layer 3 — runtime scope injection | Not started |  |  | D019 | D019 | 2.0h
20 |  | 1 | Domain Model & Database | Tenancy | Repository: users and merchant_users | Scoped repository + role assignment | Role assignment restricted to OWNER | Role changes are audit-logged and notified | Not started |  |  | D020 | D020 | 2.0h
21 |  | 1 | Domain Model & Database | Tenancy | Cross-tenant isolation test generator | Suite generated from repository interfaces | New repository method without a test fails the build | THE critical control. Never waivable | Not started |  |  | D021 | D021 | 2.5h
22 |  | 1 | Domain Model & Database | Schema build-out | Schema: catalog | listings (mode discriminator, immutable), listing_variants | Mode CHECK constraints reject invalid mode-specific fields | Mode immutability prevents capacity-strategy confusion | Not started |  |  | D022 | D022 | 2.0h
23 |  | 1 | Domain Model & Database | Schema build-out | Service: listings | Create/update/archive with mode validation | Attempt to change mode after creation is rejected | Authorization asserted at service layer, not controller | Not started |  |  | D023 | D023 | 2.0h
24 |  | 1 | Domain Model & Database | Schema build-out | Schema: inventory | inventory_units, inventory_movements (append-only) | Movement ledger sums correctly; no mutable counter | Ledger is auditable — every change has actor and reason | Not started |  |  | D024 | D024 | 2.0h
25 |  | 1 | Domain Model & Database | Schema build-out | Schema: service capacity | resources, availability_rules, availability_exceptions | Rules and exceptions persist and query correctly | Resource capacity bounds concurrent bookings | Not started |  |  | D025 | D025 | 4.0h
26 |  | 1 | Domain Model & Database | Schema build-out | Schema: reservations | reservations with state, expires_at, blocking-state index | Index present; blocking-state filter works | The correctness centre — see 05 | Not started |  |  | D026 | D026 | 2.0h
27 |  | 1 | Domain Model & Database | Schema build-out | Schema: orders | orders, order_lines with copied prices and mode | Archiving a listing does not alter historical orders | Prices copied not referenced — history must not mutate | Not started |  |  | D027 | D027 | 2.0h
28 |  | 1 | Domain Model & Database | Schema build-out | Schema: payments | payments, deposit_authorizations | provider_ref unique constraint enforced | No PAN, CVV, or track data anywhere in the schema | Not started |  |  | D028 | D028 | 4.5h
29 |  | 1 | Domain Model & Database | Schema build-out | Schema: rental lifecycle | fulfillment_events, condition_reports, condition_media, damage_claims | All tables migrate; FKs enforced | condition_media.sha256 present for tamper evidence | Not started |  |  | D029 | D029 | 2.0h
30 |  | 1 | Domain Model & Database | Schema build-out | Audit log and hash chain — GATE G1 | audit_log with prev_hash/row_hash; verification job | Tampering with a row is detected by the verifier; G1 isolation suite green | Hash chain makes tampering detectable, not merely difficult | Not started |  |  | D030 | D030 | 3.5h
31 |  | 2 | Catalog & Product Inventory | Domain + API foundation | Domain: money and line totals | Money arithmetic; invariant I8 | Property test: qty x unit price equals line total, in minor units | No floating point anywhere in money paths | Not started |  |  | D031 | D031 | 2.0h
32 |  | 2 | Catalog & Product Inventory | Domain + API foundation | Service: product listings | Create/update/archive PRODUCT listings | Mode-specific validation rejects service/rental fields | Authorization asserted before any write | Not started |  |  | D032 | D032 | 1.5h
33 |  | 2 | Catalog & Product Inventory | Domain + API foundation | Service: variants | Variant CRUD with mode-conditional fields | CHECK constraints hold for each mode | Variant price is server-authoritative | Not started |  |  | D033 | D033 | 1.5h
34 |  | 2 | Catalog & Product Inventory | Domain + API foundation | Contracts package | Zod schemas for listings and variants; generated types | Web and mobile compile against generated types | One validation definition, enforced everywhere | Not started |  |  | D034 | D034 | 1.5h
35 |  | 2 | Catalog & Product Inventory | Domain + API foundation | API skeleton | Fastify; RFC 9457 errors; X-Request-Id; structured JSON logging | Health and ready endpoints respond | No PII, tokens, or stack traces in logs or responses | Not started |  |  | D035 | D035 | 3.5h
36 |  | 2 | Catalog & Product Inventory | Domain + API foundation | API: authentication middleware | Token verification; TenantContext resolution | Invalid token rejected; ctx populated correctly | Short-lived tokens; refresh rotation with reuse detection | Not started |  |  | D036 | D036 | 1.5h
37 |  | 2 | Catalog & Product Inventory | Domain + API foundation | API: RBAC | assertCan(ctx, action, resource); role matrix | Each role's permitted and forbidden actions tested | Default deny — unlisted actions are forbidden | Not started |  |  | D037 | D037 | 1.5h
38 |  | 2 | Catalog & Product Inventory | Domain + API foundation | API: listing endpoints | CRUD routes with contract validation | Authorization test per route; cross-tenant read returns 404 | IDOR test: another merchant's listing ID is not readable | Not started |  |  | D038 | D038 | 2.0h
39 |  | 2 | Catalog & Product Inventory | Inventory | Inventory receipts and stock summation | RECEIPT movements; stock computed from ledger | Stock matches ledger sum across mixed movements | Adjustments are audit-logged with a reason | Not started |  |  | D039 | D039 | 1.5h
40 |  | 2 | Catalog & Product Inventory | Inventory | Stock invariant I5 | Guarded decrement; concurrent test N=50 | Stock never negative; exactly N succeed | Real parallel transactions, not sequential calls | Not started |  |  | D040 | D040 | 4.0h
41 |  | 2 | Catalog & Product Inventory | Inventory | Inventory units | Serialized vs fungible; status transitions | SOLD/RETIRED transitions enforced | Unit status changes audit-logged | Not started |  |  | D041 | D041 | 1.5h
42 |  | 2 | Catalog & Product Inventory | Inventory | Product sale path | Sale service; server-side price computation | Client-supplied price is ignored and the server value used | THREAT: price tampering. Prices never accepted from the client | Not started |  |  | D042 | D042 | 1.5h
43 |  | 2 | Catalog & Product Inventory | Inventory | Cart and order model | Create cart, add product line, compute totals | Totals recomputed server-side on every mutation | Cart is server-authoritative | Not started |  |  | D043 | D043 | 1.5h
44 |  | 2 | Catalog & Product Inventory | Inventory | Product purchase E2E — GATE G2 | End-to-end product purchase test | A product can be listed, stocked, and sold unaided | G2 record filed with test evidence | Not started |  |  | D044 | D044 | 3.0h
45 |  | 3 | Availability Engine & Services | Availability domain | Interval type and overlap predicate | Half-open [start,end) type; overlap function in packages/domain | Adjacent intervals do not conflict; 1-second overlap does | Pure function, no I/O — unit tested exhaustively | Not started |  |  | D045 | D045 | 2.5h
46 |  | 3 | Availability Engine & Services | Availability domain | Availability rule expansion | weekday + time window to concrete intervals | DST transition cases produce correct local windows | Timezone errors are a correctness risk (T23) | Not started |  |  | D046 | D046 | 2.5h
47 |  | 3 | Availability Engine & Services | Availability domain | Availability exceptions | BLACKOUT and EXTRA application | Exception overrides base rule correctly | Merchant-controlled, tenant-scoped | Not started |  |  | D047 | D047 | 2.5h
48 |  | 3 | Availability Engine & Services | Availability domain | Free-interval computation | rules minus exceptions minus blocking reservations | Computed free set matches fixtures across edge cases | Never returns who booked a slot — free/busy only | Not started |  |  | D048 | D048 | 2.5h
49 |  | 3 | Availability Engine & Services | Reservation engine | Reservation repository | Blocking-state query with overlap predicate | Query uses the index; returns only HELD/CONFIRMED/IN_USE | Blocking-state filter is security-relevant: expired holds must not block | Not started |  |  | D049 | D049 | 2.5h
50 |  | 3 | Availability Engine & Services | Reservation engine | SQLite write path | BEGIN IMMEDIATE check-then-insert | Deferred-transaction variant demonstrably fails; IMMEDIATE passes | BEGIN IMMEDIATE is load-bearing — deferred allows the race | Not started |  |  | D050 | D050 | 4.5h
51 |  | 3 | Availability Engine & Services | Reservation engine | PostgreSQL exclusion constraint | btree_gist; EXCLUDE USING gist migration with state predicate | Constraint rejects an overlapping insert at the database level | Makes double-booking impossible even from a console session | Not started |  |  | D051 | D051 | 5.5h
52 |  | 3 | Availability Engine & Services | Reservation engine | Concurrency test harness | Real parallel transaction runner for both dialects | Harness demonstrably races (fails without the fix) | A test that isn't actually concurrent proves nothing | Not started |  |  | D052 | D052 | 5.5h
53 |  | 3 | Availability Engine & Services | Reservation engine | Concurrency suite: identical reservations | N=50 parallel identical requests, both dialects | Exactly one succeeds on each dialect | GATE G3 core test — never waivable | Not started |  |  | D053 | D053 | 5.5h
54 |  | 3 | Availability Engine & Services | Reservation engine | Concurrency suite: edge cases | Adjacent, 1-second overlap, capacity>1 resource | Adjacent both succeed; overlap rejected; capacity-3 admits exactly 3 | Capacity path uses SELECT FOR UPDATE on the resource row | Not started |  |  | D054 | D054 | 4.5h
55 |  | 3 | Availability Engine & Services | Reservation engine | Reservation state machine | Domain state machine with transition guards | Illegal transitions rejected; terminal states enforced | State is never written directly — events drive transitions | Not started |  |  | D055 | D055 | 2.5h
56 |  | 3 | Availability Engine & Services | Reservation engine | Hold expiry | expires_at; lazy filter in every overlap query | Expired hold does not block before the sweeper runs | Lazy filter guarantees correctness independent of the job | Not started |  |  | D056 | D056 | 2.5h
57 |  | 3 | Availability Engine & Services | Reservation engine | Sweeper job | Scheduled expiry of holds; releases authorizations | Idempotent; safe under concurrent runs | Releases customer money promptly rather than letting holds lapse | Not started |  |  | D057 | D057 | 4.5h
58 |  | 3 | Availability Engine & Services | Services | Resources and availability rules service | CRUD for resources, rules, exceptions | Tenant-scoped; authorization tested | Staff resources contain personal data — classified in 08 | Not started |  |  | D058 | D058 | 2.5h
59 |  | 3 | Availability Engine & Services | Services | Service booking creation | HELD to CONFIRMED flow for SERVICE mode | Booking occupies the resource; conflict rejected | Idempotency-Key required on creation | Not started |  |  | D059 | D059 | 2.5h
60 |  | 3 | Availability Engine & Services | Services | Availability API endpoint | GET availability with 90-day cap, caching, invalidation | Cache invalidated on any reservation write for that subject | Unauthenticated — tightest rate limit in the system | Not started |  |  | D060 | D060 | 2.5h
61 |  | 3 | Availability Engine & Services | Services | Service booking endpoints | Booking routes + privacy test | Response never contains another customer's identity | THREAT: information disclosure via availability response | Not started |  |  | D061 | D061 | 2.5h
62 |  | 3 | Availability Engine & Services | Services | Hold exhaustion limits — GATE G3 | Per-IP and per-account concurrent-hold caps | Anonymous cart cap enforced; abandonment monitored | THREAT: DoS by reserving all inventory without paying | Not started |  |  | D062 | D062 | 6.0h
63 |  | 4 | Rentals, Deposits & Returns | Rental core | Rental variant fields | rate_period, deposit_minor, buffer_minutes | Mode CHECK constraints enforce rental-only fields | Deposit amount is server-authoritative | Not started |  |  | D063 | D063 | 4.5h
64 |  | 4 | Rentals, Deposits & Returns | Rental core | Buffer expansion | Interval expanded at write time; buffer stored on reservation | Later variant buffer change does not alter existing bookings | Stored buffer prevents retroactive schedule mutation | Not started |  |  | D064 | D064 | 3.0h
65 |  | 4 | Rentals, Deposits & Returns | Rental core | Unit allocator | Least-recently-returned-first selection | Allocation spreads across fleet; deterministic under test | Even wear and even utilization data | Not started |  |  | D065 | D065 | 3.0h
66 |  | 4 | Rentals, Deposits & Returns | Rental core | Rental reservation creation | Reservation against a serialized inventory unit | Conflict rejected; allocator picks a free unit | Idempotency-Key required | Not started |  |  | D066 | D066 | 3.0h
67 |  | 4 | Rentals, Deposits & Returns | Rental core | Invariant I3: rented unit cannot be sold | Sale-path check against blocking reservations | Selling a currently-rented unit is rejected | The invariant no competitor implements | Not started |  |  | D067 | D067 | 3.5h
68 |  | 4 | Rentals, Deposits & Returns | Rental core | Invariant I4: sold unit cannot be reserved | Reservation-path status check | Reserving a SOLD or RETIRED unit is rejected | Prevents renting an asset the merchant no longer owns | Not started |  |  | D068 | D068 | 3.5h
69 |  | 4 | Rentals, Deposits & Returns | Rental core | Future-reservation sale override | Warn, require explicit override, cancel and notify | Override path cancels affected bookings and notifies customers | Override is audit-logged with actor and reason | Not started |  |  | D069 | D069 | 3.0h
70 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Fulfillment events | PICKED_UP and RETURNED event handlers | Events recorded append-only with actor | Event log is repudiation defence | Not started |  |  | D070 | D070 | 3.0h
71 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Event-driven state transitions | Reservation state moves via events only | Direct state write is rejected by the service layer | Single path for state change simplifies audit | Not started |  |  | D071 | D071 | 3.0h
72 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Condition report: checkout | CHECKOUT phase report required before IN_USE (I7) | Transition to IN_USE without a report is rejected | Without a baseline, a damage claim is unwinnable | Not started |  |  | D072 | D072 | 4.5h
73 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Condition media upload | Signed upload URLs; content-type and size limits | Oversized and wrong-type uploads rejected | Private bucket, randomized keys, no public access | Not started |  |  | D073 | D073 | 3.0h
74 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Condition media integrity | SHA-256 recorded at upload; keys never overwritten | Hash mismatch detected; overwrite attempt rejected | THREAT: tampering with dispute evidence | Not started |  |  | D074 | D074 | 3.0h
75 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Condition report: check-in | CHECKIN phase with condition grade comparison | Grade delta surfaced to merchant | Both-phase evidence supports or defeats a claim fairly | Not started |  |  | D075 | D075 | 4.5h
76 |  | 4 | Rentals, Deposits & Returns | Lifecycle | Damage claim | Create, state machine, customer notification | Claim states transition legally; customer notified | Customer can see and respond to a claim against them | Not started |  |  | D076 | D076 | 4.5h
77 |  | 4 | Rentals, Deposits & Returns | Deposits | Deposit state machine | Domain machine: AUTHORIZED to RELEASED/CAPTURED/PARTIAL/EXPIRED | Illegal transitions rejected | Every transition audit-logged | Not started |  |  | D077 | D077 | 4.5h
78 |  | 4 | Rentals, Deposits & Returns | Deposits | Single-capture and bounds | One capture attempt; amount bounded by authorization | Second capture rejected; over-capture rejected | THREAT: deposit amount tampering. Critical control | Not started |  |  | D078 | D078 | 4.5h
79 |  | 4 | Rentals, Deposits & Returns | Deposits | Authorization window ceiling | Provider window recorded; rental term validated against it | Rental beyond the window is rejected at configuration with guidance | Product constraint surfaced in UI, not discovered in production | Not started |  |  | D079 | D079 | 3.0h
80 |  | 4 | Rentals, Deposits & Returns | Deposits | Deposit auto-release job | Scheduled release when completed with no claim | Hold released before expiry; customer notified | Never let a hold silently lapse on a customer's card | Not started |  |  | D080 | D080 | 4.5h
81 |  | 4 | Rentals, Deposits & Returns | Exceptions | Late return detection | Overdue derived state; merchant and customer notified | Overdue detected without a stored state field | Overdue is derived — no state drift | Not started |  |  | D081 | D081 | 3.0h
82 |  | 4 | Rentals, Deposits & Returns | Exceptions | Downstream conflict alerts | Detect and alert on affected following bookings | Alert names the specific affected booking and contact | A late return is a double-booking that already happened | Not started |  |  | D082 | D082 | 3.0h
83 |  | 4 | Rentals, Deposits & Returns | Exceptions | Late fee policy | Applied on merchant confirmation, not automatically | No automatic charge without merchant action | Automatic charging without review invites chargebacks | Not started |  |  | D083 | D083 | 3.0h
84 |  | 4 | Rentals, Deposits & Returns | Exceptions | Rental cancellation and refunds | Per-mode cancellation policy configuration | Product, service, and rental policies configured separately | Three different policies, never forced into one rule | Not started |  |  | D084 | D084 | 3.0h
85 |  | 4 | Rentals, Deposits & Returns | Exceptions | Media retention job | 90-day / 2-year retention with dry-run and deletion audit | Dry run lists correctly; deletion writes an audit record | Retention set when the feature ships, not deferred | Not started |  |  | D085 | D085 | 3.0h
86 |  | 4 | Rentals, Deposits & Returns | Exceptions | Rental lifecycle E2E — GATE G4 | Full lifecycle test: reserve, checkout, use, return, settle | All invariants I3, I4, I7 hold end to end | G4 record filed with test evidence | Not started |  |  | D086 | D086 | 5.0h
87 |  | 5 | Payments — Stripe Connect | Stripe Connect | Connect platform setup | Platform account; connected-account onboarding flow | A test merchant completes onboarding | Provider holds funds — reduces money-transmitter exposure | Not started |  |  | D087 | D087 | 2.5h
88 |  | 5 | Payments — Stripe Connect | Stripe Connect | Payments schema wiring | Payment records; provider_ref uniqueness | Duplicate provider_ref rejected | provider_ref is the idempotency anchor | Not started |  |  | D088 | D088 | 3.5h
89 |  | 5 | Payments — Stripe Connect | Stripe Connect | Checkout PaymentIntent | Intent creation with application-fee split | Split lands correctly on a test transaction | Amounts computed server-side only | Not started |  |  | D089 | D089 | 3.5h
90 |  | 5 | Payments — Stripe Connect | Stripe Connect | Idempotency keys | Required on all money-moving and reservation POSTs | Replayed request returns the original result, no duplicate | Mobile retries on poor connections — non-negotiable | Not started |  |  | D090 | D090 | 2.5h
91 |  | 5 | Payments — Stripe Connect | Webhooks | Webhook signature verification | Verify before parse; discard and log unverified | Unsigned and wrongly-signed events rejected | CRITICAL threat: forged webhook triggering deposit release | Not started |  |  | D091 | D091 | 5.0h
92 |  | 5 | Payments — Stripe Connect | Webhooks | Webhook idempotency | Dedupe by provider event id; persist raw event | Duplicate delivery processed once | Providers retry aggressively | Not started |  |  | D092 | D092 | 3.5h
93 |  | 5 | Payments — Stripe Connect | Webhooks | Webhook ordering tolerance | Out-of-order handling; async processing; fast 200 | Out-of-order sequence produces correct final state | Ordering is not guaranteed by the provider | Not started |  |  | D093 | D093 | 3.5h
94 |  | 5 | Payments — Stripe Connect | Deposits and refunds | Authorization via provider | Manual-capture PaymentIntent for deposits | Hold placed; expiry recorded from provider response | expires_at mandatory — drives the auto-release job | Not started |  |  | D094 | D094 | 5.0h
95 |  | 5 | Payments — Stripe Connect | Deposits and refunds | Capture, partial capture, release | Provider calls wired to the deposit state machine | Partial capture releases remainder; state correct | Single capture enforced at both domain and provider layers | Not started |  |  | D095 | D095 | 4.0h
96 |  | 5 | Payments — Stripe Connect | Deposits and refunds | Refunds per mode | Product, service, and rental refund paths | Each mode's policy applied correctly | Refund authority restricted by role | Not started |  |  | D096 | D096 | 2.5h
97 |  | 5 | Payments — Stripe Connect | Deposits and refunds | Payout reconciliation view | Merchant-facing payout and fee breakdown | Figures reconcile against provider records | Reconciliation mismatch is an escalation trigger (T3) | Not started |  |  | D097 | D097 | 2.5h
98 |  | 5 | Payments — Stripe Connect | Deposits and refunds | Payment failure handling | Retry and customer-facing error mapping | Declines produce actionable, non-leaky messages | Error text reveals nothing about the payment method | Not started |  |  | D098 | D098 | 3.5h
99 |  | 5 | Payments — Stripe Connect | Deposits and refunds | PCI SAQ A verification | Automated test asserting no card fields in our DOM | Test fails if a card input is added to our pages | Preserves SAQ A eligibility — change requires an ADR | Not started |  |  | D099 | D099 | 2.5h
100 |  | 5 | Payments — Stripe Connect | Deposits and refunds | Payments E2E — GATE G5 | End-to-end money movement across all three modes | Charges, splits, deposits, and refunds all correct | G5 record filed with test evidence | Not started |  |  | D100 | D100 | 6.5h
101 |  | 6 | Merchant Dashboard (Web) | Dashboard foundation | Next.js scaffold and auth | App shell, protected routes, session handling | Unauthenticated access redirects; role gates work | Tokens in memory + httpOnly refresh cookie, never localStorage | Not started |  |  | D101 | D101 | 2.0h
102 |  | 6 | Merchant Dashboard (Web) | Dashboard foundation | Design system | Tokens, base components, accessible forms | Keyboard navigation and labels verified | Output encoding by default; strict CSP, no unsafe-inline | Not started |  |  | D102 | D102 | 2.0h
103 |  | 6 | Merchant Dashboard (Web) | Dashboard foundation | Merchant onboarding | Account, business profile, location setup | A new merchant completes setup unaided | Seller identity captured at onboarding (DAC7/DSA readiness) | Not started |  |  | D103 | D103 | 2.0h
104 |  | 6 | Merchant Dashboard (Web) | Dashboard foundation | Connect onboarding UI | Stripe onboarding embedded flow | Merchant reaches payouts-enabled state | No bank details stored by us | Not started |  |  | D104 | D104 | 3.0h
105 |  | 6 | Merchant Dashboard (Web) | Catalog management | Catalog list view | Mixed-mode list with filters by mode and status | All three modes visible in one view | Tenant-scoped query; no cross-merchant leakage | Not started |  |  | D105 | D105 | 2.0h
106 |  | 6 | Merchant Dashboard (Web) | Catalog management | Listing editor: product | Create and edit PRODUCT listings and variants | Product with variants saves and renders | Server-side validation mirrors client Zod schema | Not started |  |  | D106 | D106 | 2.0h
107 |  | 6 | Merchant Dashboard (Web) | Catalog management | Listing editor: service | SERVICE listings: duration, resources, policy | Service bookable after save | Resource assignment respects tenant scope | Not started |  |  | D107 | D107 | 2.0h
108 |  | 6 | Merchant Dashboard (Web) | Catalog management | Listing editor: rental | RENTAL listings: rate period, deposit, buffer | Deposit and buffer persist and apply | Window-ceiling warning shown for long rental terms | Not started |  |  | D108 | D108 | 3.5h
109 |  | 6 | Merchant Dashboard (Web) | Catalog management | Variant management | Variant table with pricing and attributes | Bulk edit works; prices validated | Price changes do not affect historical orders | Not started |  |  | D109 | D109 | 2.0h
110 |  | 6 | Merchant Dashboard (Web) | Inventory and calendar | Inventory unit management | List, add, edit, retire units; acquisition cost capture | Units tracked individually for rentals | Acquisition data captured now — impossible to backfill | Not started |  |  | D110 | D110 | 2.0h
111 |  | 6 | Merchant Dashboard (Web) | Inventory and calendar | Rental status on units | Unit list shows out-on-rental with return date | A rented unit is visibly unavailable for sale | THE demo moment — shared inventory made visible | Not started |  |  | D111 | D111 | 2.0h
112 |  | 6 | Merchant Dashboard (Web) | Inventory and calendar | Resources and availability editor | Weekly rules per resource | Availability renders correctly in merchant timezone | Timezone handling verified across DST | Not started |  |  | D112 | D112 | 2.0h
113 |  | 6 | Merchant Dashboard (Web) | Inventory and calendar | Availability exceptions UI | Blackouts and extra openings | Exception blocks or opens the expected window | Merchant-scoped only | Not started |  |  | D113 | D113 | 2.0h
114 |  | 6 | Merchant Dashboard (Web) | Inventory and calendar | Unified calendar | Bookings and rentals in one view, filterable | All modes on one calendar; conflicts highlighted | No customer data beyond what staff need | Not started |  |  | D114 | D114 | 2.0h
115 |  | 6 | Merchant Dashboard (Web) | Operations | Order list and detail | Cross-mode order management | Orders from all three modes render correctly | Role-gated: READ_ONLY cannot mutate | Not started |  |  | D115 | D115 | 2.0h
116 |  | 6 | Merchant Dashboard (Web) | Operations | Rental check-out flow | Condition report with photo capture | Cannot complete checkout without a report | Photograph the asset, not the customer — guidance in UI | Not started |  |  | D116 | D116 | 3.5h
117 |  | 6 | Merchant Dashboard (Web) | Operations | Rental check-in flow | Check-in report with side-by-side comparison | Grade delta surfaced; unit returns to availability | Media integrity hash verified on display | Not started |  |  | D117 | D117 | 2.0h
118 |  | 6 | Merchant Dashboard (Web) | Operations | Damage claim UI | File, review, capture or waive | Capture bounded by authorized amount in the UI | Capture requires explicit confirmation — one attempt only | Not started |  |  | D118 | D118 | 3.5h
119 |  | 6 | Merchant Dashboard (Web) | Operations | Deposit management view | Held, released, captured, expiring soon | Expiring holds surfaced before they lapse | Prevents silent expiry on customer cards | Not started |  |  | D119 | D119 | 3.5h
120 |  | 6 | Merchant Dashboard (Web) | Operations | Settings and team — GATE G6 | Policies, notifications, team roles | A merchant completes a full operating cycle unaided | Role changes audit-logged and notified to owners | Not started |  |  | D120 | D120 | 3.5h
121 |  | 7 | Customer Storefront (Web) | Storefront | Public merchant page | Mixed catalog rendering across three modes | All three modes visible on one page | Public endpoint — rate limited, no internal IDs exposed | Not started |  |  | D121 | D121 | 2.0h
122 |  | 7 | Customer Storefront (Web) | Storefront | Listing detail: product | Product page with variants and stock state | Out-of-stock reflected accurately | Stock state never reveals exact competitor-sensitive counts | Not started |  |  | D122 | D122 | 2.0h
123 |  | 7 | Customer Storefront (Web) | Storefront | Listing detail: service | Service page with slot picker | Only free slots selectable | Availability shows free/busy only, never who booked | Not started |  |  | D123 | D123 | 2.0h
124 |  | 7 | Customer Storefront (Web) | Storefront | Listing detail: rental | Rental page with date-range picker and deposit disclosure | Unavailable ranges blocked; deposit shown before checkout | Deposit disclosed before any commitment | Not started |  |  | D124 | D124 | 3.5h
125 |  | 7 | Customer Storefront (Web) | Storefront | Availability calendar UI | Free-interval display with month navigation | Matches server availability exactly | 90-day request cap respected by the client | Not started |  |  | D125 | D125 | 2.0h
126 |  | 7 | Customer Storefront (Web) | Cart and checkout | Mixed-mode cart | Cart holding product, service, and rental lines | All three line types coexist and total correctly | Totals always recomputed server-side | Not started |  |  | D126 | D126 | 2.0h
127 |  | 7 | Customer Storefront (Web) | Cart and checkout | Hold countdown | Visible expiry timer; graceful expiry handling | Expired hold produces a clear recoverable error | Prevents silent loss of a slot at payment time | Not started |  |  | D127 | D127 | 5.0h
128 |  | 7 | Customer Storefront (Web) | Cart and checkout | Checkout: details and consent | Customer details; terms consent with version and timestamp | Consent recorded with terms version | Repudiation defence: consent is evidenced | Not started |  |  | D128 | D128 | 2.0h
129 |  | 7 | Customer Storefront (Web) | Cart and checkout | Checkout: deposit consent | Explicit deposit authorization disclosure and consent | Customer sees hold amount, duration, and conditions | Clear disclosure reduces dispute and chargeback risk | Not started |  |  | D129 | D129 | 3.5h
130 |  | 7 | Customer Storefront (Web) | Cart and checkout | Payment UI | Stripe hosted fields integration | Payment completes; no card data in our DOM | SAQ A test passes against the live checkout page | Not started |  |  | D130 | D130 | 3.0h
131 |  | 7 | Customer Storefront (Web) | Cart and checkout | Order confirmation | Confirmation page and emailed receipt | Receipt itemizes charges and any deposit hold | No card details in the receipt | Not started |  |  | D131 | D131 | 3.5h
132 |  | 7 | Customer Storefront (Web) | Customer account | Order history | Past and upcoming across modes | Only the authenticated customer's orders are returned | IDOR test: another customer's order ID returns 404 | Not started |  |  | D132 | D132 | 2.0h
133 |  | 7 | Customer Storefront (Web) | Customer account | Cancellation flow | Per-mode cancellation with policy application | Correct refund and deposit release per policy | Cancellation authority verified against ownership | Not started |  |  | D133 | D133 | 3.5h
134 |  | 7 | Customer Storefront (Web) | Customer account | Transactional notifications | Confirmation, reminder, return-due, deposit release | All four delivered in test | Transactional only — no marketing, so no consent management | Not started |  |  | D134 | D134 | 3.5h
135 |  | 7 | Customer Storefront (Web) | Customer account | Accessibility and responsive pass | WCAG AA basics; mobile-web layout | Keyboard and screen-reader paths verified | Accessible error messaging does not leak detail | Not started |  |  | D135 | D135 | 2.0h
136 |  | 7 | Customer Storefront (Web) | Customer account | E2E suite and MVP GATE G7 | Five critical flows in Playwright | All five pass; platform is pilot-capable | G7 record filed — MVP gate | Not started |  |  | D136 | D136 | 3.5h
137 |  | 8 | Mobile Application | Mobile foundation | Expo scaffold | App shell wired to shared contracts package | Builds for iOS and Android simulators | Shared Zod schemas — one validation definition | Not started |  |  | D137 | D137 | 2.0h
138 |  | 8 | Mobile Application | Mobile foundation | Mobile authentication | OIDC PKCE; tokens in Keychain/Keystore | Sign-in and refresh work on both platforms | Never AsyncStorage for tokens — platform secure storage only | Not started |  |  | D138 | D138 | 2.0h
139 |  | 8 | Mobile Application | Mobile foundation | Navigation and design parity | Navigation structure and component parity | Core screens match web behaviour | No server-side logic leaked into the client bundle | Not started |  |  | D139 | D139 | 2.0h
140 |  | 8 | Mobile Application | Mobile customer flows | Merchant discovery and page | Merchant profile screen | Mixed catalog renders on mobile | Public endpoints rate-limited per device | Not started |  |  | D140 | D140 | 2.0h
141 |  | 8 | Mobile Application | Mobile customer flows | Catalog browse | Mixed-mode listing browse with filters | All three modes browsable | Pagination cursor-based, no offset leakage | Not started |  |  | D141 | D141 | 2.0h
142 |  | 8 | Mobile Application | Mobile customer flows | Listing detail: product | Mobile product screen | Purchase path reaches checkout | Prices fetched server-side, never cached stale | Not started |  |  | D142 | D142 | 2.0h
143 |  | 8 | Mobile Application | Mobile customer flows | Listing detail: service | Slot picker on mobile | Only free slots selectable | Free/busy only | Not started |  |  | D143 | D143 | 2.0h
144 |  | 8 | Mobile Application | Mobile customer flows | Listing detail: rental | Date-range picker with deposit disclosure | Deposit terms shown before checkout | Disclosure parity with web | Not started |  |  | D144 | D144 | 3.5h
145 |  | 8 | Mobile Application | Mobile customer flows | Mobile cart and holds | Cart with hold countdown | Hold expiry handled gracefully offline and online | Idempotency keys on all creation calls | Not started |  |  | D145 | D145 | 4.0h
146 |  | 8 | Mobile Application | Mobile customer flows | Mobile checkout | Stripe mobile SDK with hosted fields | Payment completes on both platforms | No card data touches our code on mobile either | Not started |  |  | D146 | D146 | 3.0h
147 |  | 8 | Mobile Application | Mobile customer flows | Order history and upcoming | Customer order screens | Only own orders returned | Ownership enforced server-side, not by client filter | Not started |  |  | D147 | D147 | 2.0h
148 |  | 8 | Mobile Application | Mobile customer flows | Push notifications | Confirmations, reminders, return-due | Delivered on both platforms | No sensitive detail in notification payloads | Not started |  |  | D148 | D148 | 2.0h
149 |  | 8 | Mobile Application | Mobile customer flows | Read caching | Offline-tolerant reads; no offline writes | Cached reads work; writes fail clearly when offline | Offline writes explicitly out of scope (accepted risk) | Not started |  |  | D149 | D149 | 2.0h
150 |  | 8 | Mobile Application | Mobile customer flows | Condition photo capture | Camera capture for merchant staff | Photos upload with hash and metadata | Camera permission requested with clear purpose string | Not started |  |  | D150 | D150 | 2.0h
151 |  | 8 | Mobile Application | Mobile customer flows | Store builds and distribution | Signing, TestFlight, Play internal testing | Internal testers can install both builds | Signing keys in Secrets Manager, never in the repo | Not started |  |  | D151 | D151 | 2.0h
152 |  | 8 | Mobile Application | Mobile customer flows | Mobile E2E — GATE G8 | Automated mobile test suite | Customer flows pass on both platforms | G8 record filed | Not started |  |  | D152 | D152 | 4.0h
153 |  | 9 | Security Hardening & Compliance Pack | Testing | Penetration test scoping | Scope, rules of engagement, engagement booked | Tester has environment access | Test against staging with synthetic data only | Not started |  |  | D153 | D153 | 2.0h
154 |  | 9 | Security Hardening & Compliance Pack | Testing | Pen test remediation round 1 | Critical and high findings fixed | All criticals closed | Each finding gets a regression test | Not started |  |  | D154 | D154 | 2.0h
155 |  | 9 | Security Hardening & Compliance Pack | Testing | Pen test remediation round 2 and retest | Remaining findings; retest clean | Retest report clean of critical/high | Retest evidence filed for control mapping | Not started |  |  | D155 | D155 | 2.0h
156 |  | 9 | Security Hardening & Compliance Pack | Testing | Load test: availability endpoint | k6 scenario at expected peak x5 | Latency within budget; cache effective | Confirms rate limits hold under load | Not started |  |  | D156 | D156 | 2.0h
157 |  | 9 | Security Hardening & Compliance Pack | Testing | Load test: reservation creation | Concurrent reservation load | No overlaps created under sustained load | The concurrency guarantee verified at scale, not just in unit tests | Not started |  |  | D157 | D157 | 4.0h
158 |  | 9 | Security Hardening & Compliance Pack | Testing | Performance remediation | Fixes from load results | Targets met on re-run | No correctness traded for speed | Not started |  |  | D158 | D158 | 2.0h
159 |  | 9 | Security Hardening & Compliance Pack | Hardening | WAF, rate limits, CSP | Rules tuned; CSP without unsafe-inline | Common attack patterns blocked; CSP violations zero | Defence in depth at the edge | Not started |  |  | D159 | D159 | 2.0h
160 |  | 9 | Security Hardening & Compliance Pack | Hardening | Alerting | Security events, error rate, latency, job failures | Test alerts fire and route correctly | Tuned to genuine impact — no rotation exists to absorb noise | Not started |  |  | D160 | D160 | 2.0h
161 |  | 9 | Security Hardening & Compliance Pack | Hardening | Hash-chain verification scheduling | Scheduled verification with alerting | Injected tamper triggers an alert | Log integrity monitoring, not just logging | Not started |  |  | D161 | D161 | 2.0h
162 |  | 9 | Security Hardening & Compliance Pack | Compliance | PCI SAQ A completion | SAQ completed; provider attestations filed | SAQ signed and stored in /docs/compliance/pci-saq-a | Eligibility conditions each evidenced by a test | Not started |  |  | D162 | D162 | 2.0h
163 |  | 9 | Security Hardening & Compliance Pack | Compliance | First access review | Roles across repo, cloud, IdP reviewed and recorded | Review record filed | SOC 2 CC6 evidence; the one recurring human control | Not started |  |  | D163 | D163 | 2.0h
164 |  | 9 | Security Hardening & Compliance Pack | Compliance | Incident response tabletop | Exercise run against a realistic scenario | Exercise record with lessons filed | A plan never exercised is a document, not a capability | Not started |  |  | D164 | D164 | 2.0h
165 |  | 9 | Security Hardening & Compliance Pack | Compliance | Evidence pack assembly | /docs/compliance/evidence populated from CI artifacts | SBOMs, scans, test results, gate records all present | Evidence by design — nothing written just for an auditor | Not started |  |  | D165 | D165 | 2.0h
166 |  | 9 | Security Hardening & Compliance Pack | Compliance | Control mapping review — GATE G9 | Mapping reviewed against NIST CSF 2.0 | Every control has a named, existing artifact | G9 record filed | Not started |  |  | D166 | D166 | 3.5h
167 |  | 10 | Pilot Readiness & Launch | Production | Terraform production stand-up | VPC, ECS, RDS Multi-AZ, Redis, S3, WAF per 11 | Environment provisioned from code | IaC is the asset-inventory evidence; RDS has no public endpoint | Not started |  |  | D167 | D167 | 1.5h
168 |  | 10 | Pilot Readiness & Launch | Production | Production deploy pipeline | Manual promotion gate; tagged releases | A release deploys and rolls back cleanly | Promotion requires explicit approval | Not started |  |  | D168 | D168 | 1.5h
169 |  | 10 | Pilot Readiness & Launch | Production | Cutover rehearsal | SQLite to PostgreSQL migration rehearsed on staging | Full suite passes unchanged against PostgreSQL | Exclusion constraint verified against real data volume | Not started |  |  | D169 | D169 | 4.5h
170 |  | 10 | Pilot Readiness & Launch | Production | Backup and restore rehearsal | Backups configured; restore performed end to end | Restore completes within the stated RTO | An untested restore is not a backup | Not started |  |  | D170 | D170 | 1.5h
171 |  | 10 | Pilot Readiness & Launch | Production | Runbooks | Failover, deposit mismatch, stuck sweeper, webhook backlog | Each runbook walked through once | Written for the failures that will actually occur | Not started |  |  | D171 | D171 | 4.0h
172 |  | 10 | Pilot Readiness & Launch | Production | Monitoring and on-call tuning | Dashboards; alert thresholds tuned | No false pages during a 48-hour soak | Alert fatigue is a real risk with no rotation | Not started |  |  | D172 | D172 | 1.5h
173 |  | 10 | Pilot Readiness & Launch | Production | Merchant onboarding materials | Walkthrough guide and support playbook | A non-technical reader can follow it | No credentials or internal URLs in merchant-facing docs | Not started |  |  | D173 | D173 | 1.5h
174 |  | 10 | Pilot Readiness & Launch | Production | Pilot merchant setup | First merchant's catalog configured with them | All three modes configured with real data | Real customer data enters the system — retention jobs must be live | Not started |  |  | D174 | D174 | 1.5h
175 |  | 10 | Pilot Readiness & Launch | Production | Soft launch | First real transactions, founder-supported | One real transaction in each mode | Monitor audit log and deposit states closely | Not started |  |  | D175 | D175 | 3.0h
176 |  | 10 | Pilot Readiness & Launch | Production | Post-launch review — GATE G10 | Review of the first live week | G10 record filed; issues triaged into a backlog | Confirm retention and audit jobs running in production | Not started |  |  | D176 | D176 | 3.0h
Formulas:
Date = WORKDAY(Config!$B5,ROUND(([Day]-1)*5/Config!$B6,0))

## Weekly Review
Weekly Review Log
60 minutes, same day each week. Record the uncomfortable items — carried cards, skipped tests, slipping dates. Restate the projected end date each week from the actual completion rate, not from the original plan.
Wk | Week of | Phase | Planned | Done | Carried | Blocked | Rate % | 4-wk rolling % | Gate status | New crit/high | Remediated | Tests skipped | Domain cov % | ADRs | Scope change (days) | Risks changed | Projected end | Top blocker next week | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62

## Escalation Triggers
Escalation Triggers
Conditions that require a decision rather than another week of the same. From 13_weekly_review_protocol.md.
Trigger | Action
Rolling completion below 60% for three weeks | Re-plan. Reduce MVP scope or add capacity — do not simply extend the end date.
The same card carried three times | It is scoped wrong or blocked on something unrecognized. Stop and decompose it.
A gate criterion failing two weeks running | Stop the phase. Fix before proceeding.
Critical scanner findings open beyond seven days | Stop feature work until remediated.
Any tenant-isolation or concurrency test skipped | STOP IMMEDIATELY. These are never optional.
Actual effort routinely exceeding planned by 50%+ | The one-day card assumption is wrong for this phase; re-scope the remaining cards.
Deposit reconciliation mismatch observed | Treat as critical (T3). Halt payment-related work until root-caused.
A production reservation overlap observed | Treat as critical (T2). Halt and root-cause before any further release.